## Overview
GrubExpress Frontend Review
Component-wise tracker ¦ Static source review; build/lint checked, no live walkthrough ¦ 2026-10-03
Overall | Count | Priority | Count
Total findings | 64 | Critical | 2
Open | 64 | High | 16
Critical + High | 18 | Medium | 34
|  | Low | 12
Finding type | Count | Type / scope | Meaning | Priority | Meaning
Confirmed defect | 29 | Confirmed defect | Specific behavior evidenced by source/build output. | Critical | Build or primary customer flow is blocked.
Incomplete feature | 8 | Incomplete feature | Visible workflow/control exists but implementation is missing. | High | Major flow, data, navigation, or admin function is broken/incomplete.
Improvement | 26 | Improvement | Hardening or quality work; not necessarily a runtime bug. | Medium | Meaningful UX, error-state, accessibility, or reliability risk.
Review required | 1 | Review required | Dependency/runtime behavior needs clean-install confirmation. | Low | Polish or maintainability improvement.

## Review Tracker
Frontend review issue tracker
Filter by component, classification, priority, or status. Update Status as fixes progress.
ID | Priority | Classification | Finding type | Component / route | Finding | Impact / suggested action | Evidence / source | Status
FE-001 | Critical | Build / TypeScript | Confirmed defect | Application build | Production build stops at TypeScript compilation. Diagnostics include unresolved names, unsupported component props, and unused declarations. | No deployable build. Fix compiler errors first; rerun build and enforce it in CI. | npm run build; src/**/*.ts(x) | Open
FE-002 | High | Hooks / Runtime | Confirmed defect | OfferContainer | Hooks are called in lowercase helper functions that are conditionally invoked; delivery and dine-out branches call different hook sequences. | Switching service type can trigger hook-order errors. Split into capitalized child components or keep hook order stable. | src/components/offers/OffersContainer.tsx | Open
FE-003 | High | Build / Component rendering | Confirmed defect | SortByMenu | JSX is not returned and sortValues/handleLocationChange are undefined. | Component renders nothing and fails type checking. Implement with defined props/state or remove it. | src/components/sortByMenu.tsx | Open
FE-004 | High | Build / UI API mismatch | Confirmed defect | LocationMenu | DropdownMenuTrigger uses unsupported asChild prop per TypeScript diagnostics. | Component fails type checking. Use the trigger API supported by installed wrapper. | src/components/customer/LocationMenu.tsx | Open
FE-005 | Medium | Build / Lint quality | Improvement | Application source | Lint reports 44 errors and 3 warnings: unused values, any, hook rules, UI fast-refresh rules. | Lint is not a reliable gate. Fix app-code issues and tune generated UI rules before using CI enforcement. | npm run lint; src/**/*.ts(x) | Open
FE-006 | High | Navigation / Auth | Confirmed defect | API response interceptor | 401 handler redirects to /login, but the app has /auth and no /login route. | Expired sessions can land on not-found. Redirect to /auth and preserve safe return path. | src/services/api.ts; src/App.tsx | Open
FE-007 | Medium | Error handling / Auth | Confirmed defect | authApi | Interceptor is attached to api, but auth and user requests use separate authApi. | Session-expiry handling differs by client. Share client configuration or add equivalent handling. | src/services/api.ts; src/services/authApi.ts | Open
FE-008 | High | Navigation / Authorization UX | Improvement | Customer/admin routes | No frontend guard checks sign-in or role before rendering protected areas. | Wrong-role/signed-out users reach screens and fail requests. Add route guards; server authorization remains required. | src/App.tsx; src/store/slices/userSlice.ts | Open
FE-009 | Medium | Error handling | Confirmed defect | SignIn and SignUp | Request failures only log; signup error state is unused and forms have no pending feedback. | Users cannot recover from failures and can resubmit. Show errors/success and disable submit while pending. | src/components/SignIn.tsx; src/components/SignUp.tsx | Open
FE-010 | Medium | Form validation | Improvement | SignIn and SignUp | Required fields omit required validation; phone accepts unrestricted text. | Malformed or blank values reach API. Add clear client validation while retaining server validation. | src/components/SignIn.tsx; src/components/SignUp.tsx | Open
FE-011 | Low | Navigation / UI polish | Confirmed defect | Auth forms | Forgot-password links point to #; signup password uses current-password autocomplete. | Recovery links do nothing; autofill hint is wrong. Implement/remove links and use new-password autocomplete. | src/components/SignIn.tsx; src/components/SignUp.tsx | Open
FE-012 | Low | Accessibility / Markup | Confirmed defect | Auth forms | Username label htmlFor mismatches its input id; sign-in nests a paragraph inside another paragraph. | Label focus and markup semantics are unreliable. Match ids and use valid text containers. | src/components/SignIn.tsx; src/components/SignUp.tsx | Open
FE-013 | Medium | Navigation / API lifecycle | Confirmed defect | NavBar | Shared navbar fetches profile/cart on mount even when signed out or when role is admin. | Unnecessary customer requests/errors on unrelated pages. Gate fetches by authenticated customer state. | src/components/NavBar.tsx | Open
FE-014 | Medium | Error handling / State | Confirmed defect | NavBar sign-out | Local state clears only after logout API succeeds. | Failed logout leaves stale signed-in UI. Clear client state safely and surface the failure. | src/components/NavBar.tsx | Open
FE-015 | High | Navigation / Admin | Confirmed defect | Admin SideMenu | Sidebar Logout button has no click handler. | Visible logout control does nothing. Wire to shared sign-out behavior. | src/components/admin/SideMenu.tsx | Open
FE-016 | Medium | UI behavior | Incomplete feature | Admin NavBar | Status dropdown, bell, and profile icon have no meaningful state/actions. | Controls imply unavailable workflows. Connect them or remove/disable until implemented. | src/components/NavBar.tsx | Open
FE-017 | Medium | Navigation / Partner onboarding | Incomplete feature | Partner page | Copy asks for phone/restaurant ID, but Continue only navigates to admin sign-in. | Prompt and action disagree. Implement lookup input or accurately describe sign-in. | src/pages/Partner.tsx | Open
FE-018 | Medium | UI behavior | Confirmed defect | Home search | Restaurant/dish search has no state, submit, filtering, or navigation. | Typing has no effect. Implement search or remove the field. | src/pages/Home.tsx | Open
FE-019 | Medium | Navigation / UI behavior | Incomplete feature | Home food categories | Food category cards do not filter or navigate. | The strip looks interactive but does nothing. Add filtering/selection or make it static. | src/components/customer/ItemsContainer.tsx | Open
FE-020 | Low | Accessibility | Confirmed defect | Home city list | City choices are clickable divs and mapped elements omit keys. | Not keyboard-operable and may emit React warnings. Use keyed buttons/links with focus states. | src/pages/Home.tsx | Open
FE-021 | Medium | State / Navigation | Confirmed defect | Location slice | removeCity sets city to empty; sign-out dispatches it. | Restaurant queries/titles can use blank city. Restore default or model unset location explicitly. | src/store/slices/locationslice.ts; src/components/NavBar.tsx | Open
FE-022 | High | Async data / State | Confirmed defect | RestaurantContainer | Old-city request can finish after city change and append results to reset list. | Feed can mix cities. Cancel obsolete requests or discard stale responses and reset pagination atomically. | src/components/restaurant/RestaurantContainer.tsx | Open
FE-023 | Medium | Error handling | Improvement | Restaurant lists | Fetch failures only log; no visible error/retry state. | Blank/partial feed gives no recovery. Add loading, empty, error, and retry states. | src/components/restaurant/RestaurantContainer.tsx; RestaurantContainerSlide.tsx | Open
FE-024 | Medium | Error handling / Navigation | Confirmed defect | RestaurantPage | No loading/error/not-found state; previous data is not cleared when route ID changes. | Can briefly show old restaurant; invalid ID looks blank. Track request state and clear/render explicit outcomes. | src/pages/customer/Restaurantpage.tsx | Open
FE-025 | Medium | Data robustness / Types | Improvement | RestaurantCard | Uses any and indexes cuisine/address fields without guards. | Missing API fields can crash. Use Restaurant types and safe fallbacks. | src/components/restaurant/RestaurantCard.tsx; src/types/restaurant.ts | Open
FE-026 | Medium | UI polish / Responsive | Improvement | Restaurant and menu layouts | Fixed viewport/card widths have little responsive adaptation. | Likely overflow/compression on phones. Use max-widths, breakpoints, flexible grids and content-driven height. | src/pages/customer/Restaurantpage.tsx; src/components/customer/menu.tsx | Open
FE-027 | Low | Maintainability | Improvement | RestaurantPage | Dine-in and delivery render functions duplicate most markup. | Fixes can drift. Extract shared details and isolate service-specific content. | src/pages/customer/Restaurantpage.tsx | Open
FE-028 | Medium | UI behavior | Confirmed defect | Menu | Top Rated and All Items accordions are open by default and show duplicate rows. | Menu repeats the same items. Default one closed or exclude featured items from the all-items list. | src/components/customer/menu.tsx | Open
FE-029 | Medium | Error handling | Improvement | Menu | Menu failure only logs; no loading/empty/retry view. | Failure looks like an empty menu. Render distinct request states. | src/components/customer/menu.tsx | Open
FE-030 | Medium | Error handling / Async UI | Improvement | ItemCard and CartItemCard | Add/remove controls lack pending state and user-facing failures. | Rapid clicks overlap requests; failures are unclear. Prevent duplicate requests and reconcile from server. | src/components/customer/ItemCard.tsx; CartItemCard.tsx | Open
FE-031 | High | State / Data consistency | Confirmed defect | cartSlice | Reducers update item rows without recomputing total; removing last row leaves restaurantId. | Totals/metadata can diverge. Derive totals or update aggregates atomically; clear restaurantId when empty. | src/store/slices/cartSlice.ts | Open
FE-032 | Critical | Checkout / Incomplete feature | Confirmed defect | Cart and Checkout | Cart proceeds directly to placeOrder; Checkout is placeholder with no working address/payment selection. | Main purchase flow cannot collect delivery info or complete payment. Implement address, server quote/order, payment and result states. | src/pages/customer/Cart.tsx; Checkout.tsx; src/services/userApi.ts | Open
FE-033 | Medium | Data / Checkout | Confirmed defect | Cart suggestions | Suggestions textarea is uncontrolled and not sent with order. | Customer instructions are discarded. Store and submit if API supports it; otherwise remove field. | src/pages/customer/Cart.tsx | Open
FE-034 | High | Pricing / Data integrity | Improvement | Cart bill summary | Delivery threshold and tax are hardcoded UI arithmetic. | Displayed amount can diverge from backend pricing/policy. Use server totals as authoritative and label estimates. | src/pages/customer/Cart.tsx | Open
FE-035 | Low | UI polish | Improvement | Cart empty state | Empty cart is plain text without a route back to browsing. | No recovery path. Add designed empty state and restaurant link. | src/pages/customer/Cart.tsx | Open
FE-036 | Medium | Error handling / UI states | Improvement | Orders page | No loading/empty/error view; fetch failure only logs. | Blank page does not distinguish no orders from failure. Render all request states and retry. | src/pages/customer/Orders.tsx | Open
FE-037 | High | Data / Order history | Confirmed defect | OrderCards | Delivered and cancelled orders render empty div. | Customers cannot review terminal order history. Render all orders and vary actions by status. | src/components/orders/OrderCards.tsx | Open
FE-038 | High | Data correctness / UI | Confirmed defect | OrderDetailsDraw | Delivery address and packaging fee are hardcoded; restaurant image is static external content. | Could show false address/charges/image. Render order/restaurant data and server-provided totals. | src/components/orders/OrderDetailsDraw.tsx | Open
FE-039 | High | Navigation / Payment | Confirmed defect | OrderCards Pay now | Navigates to payments without order ID; destination is unimplemented. | Cannot resume a specific pending payment. Pass ID and implement payment retrieval/result flow. | src/components/orders/OrderCards.tsx; Checkout.tsx | Open
FE-040 | Medium | UI behavior | Incomplete feature | OrderCards actions | Reorder, Feedback, and Help are styled divs without handlers/semantics. | Static labels look interactive. Implement accessible actions or render plain text. | src/components/orders/OrderCards.tsx | Open
FE-041 | Medium | Performance / API design | Improvement | OrderCards | Each card fetches restaurant and payment details in separate sequential calls. | Many requests for long history. Include details with order or batch calls. | src/components/orders/OrderCards.tsx; src/services/userApi.ts | Open
FE-042 | High | Admin / Incomplete feature | Incomplete feature | AdminDashboard and AdminResBanner | Stats are hardcoded zero and dashboard tables receive empty arrays. | Admins cannot see live operations. Connect restaurant-scoped APIs and request states. | src/pages/admin/AdminDashboard.tsx; AdminResBanner.tsx | Open
FE-043 | Medium | Admin / UI behavior | Confirmed defect | AdminDetailDisplay | Filter buttons change local state but do not filter; DatePicker only changes local date. | Controls promise filtering but results do not change. Apply values to query/table or remove controls. | src/pages/admin/AdminDetailDisplay.tsx; src/components/genericUIcomponents/DatePicker.tsx | Open
FE-044 | High | Admin / Data rendering | Confirmed defect | AdminTable | tableData is ignored; literal placeholder cells are rendered and map callbacks omit keys. | Admin tables cannot show real records. Type rows, render actual fields, add empty state and stable keys. | src/components/admin/AdminTable.tsx | Open
FE-045 | Medium | Admin / Error handling | Incomplete feature | AdminServiceUpdates | Counts/lists are sample data; refresh has no handler; list entries lack keys. | Activity is misleading and refresh inert. Fetch live data and wire refresh/error/loading. | src/components/admin/AdminServiceUpdates.tsx; AdminlistCards.tsx | Open
FE-046 | High | Admin / Navigation | Confirmed defect | AdminMenu Add Item | Add Item navigates to /admin/menu/items, which only renders Admin Item. | Primary CTA dead-ends. Implement form/save route or disable CTA. | src/pages/admin/AdminMenu.tsx; src/pages/admin/AdminItems.tsx | Open
FE-047 | High | Admin / Incomplete feature | Incomplete feature | ItemsEditDraw | Edit drawer has blank details and no usable form/save mutation. | Owners cannot edit despite Edit control. Bind fields, validate, submit and refresh menu. | src/components/admin/ItemsEditDraw.tsx; AdminItemCards.tsx | Open
FE-048 | Medium | Admin / Navigation | Incomplete feature | AdminRestaurant, AdminSettings, Profile | These routes render empty or placeholder content. | Visible navigation reaches unfinished screens. Complete or remove entries until ready. | src/pages/admin/AdminRestaurant.tsx; AdminSettings.tsx; src/pages/customer/profile.tsx; src/App.tsx | Open
FE-049 | Low | Navigation / UI polish | Improvement | Breadcrumbs and PublicLayout | Breadcrumbs use browser anchors and Back assigns window.location.href. | Full page reloads and raw IDs in breadcrumb. Use React Router and friendly labels. | src/components/genericUIcomponents/BreadCrumbs.tsx; src/layouts/PublicLayout.tsx | Open
FE-050 | Medium | Accessibility | Improvement | Home, Cart, AdminHome, carousels | Some actions use clickable divs; carousel arrows lack accessible names. | Keyboard/screen-reader operation is poor. Use buttons/links, aria-labels and visible focus styles. | src/pages/Home.tsx; AdminHome.tsx; Cart.tsx; ItemsContainer.tsx; RestaurantContainerSlide.tsx | Open
FE-051 | Medium | UI polish / Responsive | Improvement | Application layouts | Fixed viewport widths/heights appear on home, auth, restaurant, cart, admin. | Likely overflow on small devices. Review mobile/tablet and use responsive sizing. | src/pages/Home.tsx; src/components/SignUp.tsx; src/pages/customer/Cart.tsx; src/layouts/AdminLayout.tsx | Open
FE-052 | Low | UI polish / Content | Improvement | RestaurantCard and offers | Placeholder copy includes x hrs/km and X-percent offers; images have no fallback. | Looks unfinished and broken URLs leave blanks. Replace with real data/remove claims and add fallbacks/alt text. | src/components/restaurant/RestaurantCard.tsx; src/components/offers/OffersContainer.tsx | Open
FE-053 | Medium | Type safety | Improvement | Cart, restaurant, order, admin | Core data components use any despite available domain types. | API/null mismatches evade compiler. Define typed response models and narrow optional values. | src/components/customer/CartItemCard.tsx; RestaurantCard.tsx; OrderDetailsDraw.tsx; AdminTable.tsx; src/types/ | Open
FE-054 | Low | Documentation | Improvement | README | README remains Vite starter text. | Setup, env, routes and API assumptions are undocumented. Add project-specific onboarding. | README.md | Open
FE-055 | Low | Code quality | Improvement | Mapped lists | Some maps use array indexes or omit keys in home/admin lists. | React warns and can reconcile incorrectly. Use stable IDs/values as keys. | src/pages/Home.tsx; src/components/admin/AdminServiceUpdates.tsx; AdminTable.tsx | Open
FE-056 | Medium | UI behavior / Offers | Confirmed defect | OfferContainer tabs | Pre-booking and Walk-in tabs change styling but content stays identical. | Tab claims filtering that does not occur. Use distinct datasets or remove control. | src/components/offers/OffersContainer.tsx | Open
FE-057 | Medium | Navigation / State | Improvement | Session bootstrap | Navbar stores username from profile but does not reconcile role from response. | Persisted/default role may mismatch server session and show wrong navigation. Hydrate both from profile. | src/components/NavBar.tsx; src/store/slices/userSlice.ts | Open
FE-058 | Low | Code quality | Improvement | App.css | Vite starter selectors remain alongside product styles and appear unused. | Dead CSS obscures active styles. Remove after confirming no route relies on it. | src/App.css | Open
FE-059 | Medium | Error handling / Loading | Improvement | AdminHome | Restaurant fetch error and loading both leave restaurantData null and display add-restaurant message. | Network failure can look like an account with no restaurants. Track loading/error/empty separately with retry. | src/pages/admin/AdminHome.tsx | Open
FE-060 | Low | UI polish | Improvement | Order cards | Order timestamps render raw API strings. | Dates may be hard to scan/locale inconsistent. Format consistently and handle missing values. | src/components/orders/OrderCards.tsx; src/types/order.ts | Open
FE-061 | Medium | Runtime / Dependency | Review required | Animation imports | Components import framer-motion while package.json declares motion; verify direct dependency and build resolution. | A clean install may fail resolving the imported package. Align imports and declared package, then verify clean install/build. | src/components/customer/ItemsContainer.tsx; src/components/restaurant/RestaurantContainerSlide.tsx; package.json | Open
FE-062 | Medium | Accessibility / DOM | Confirmed defect | AdminItemCard | The Edit drawer trigger button is nested inside an outer button. | Invalid nested interactive elements can cause inconsistent activation and accessibility behavior. Use one trigger button only. | src/components/admin/AdminItemCards.tsx | Open
FE-063 | Medium | Data / Payment state | Improvement | OrderCards payment timer | Timer reaches zero locally but does not refresh payment/order status from the server. | UI may continue showing stale PENDING data. Refresh status at expiry or fetch current status on payment action. | src/components/orders/OrderCards.tsx | Open
FE-064 | Low | UI polish | Improvement | Partner page | Brand copy says SWIFFY while app branding is Grub Express; application copy also contains spelling/demo text. | Inconsistent brand/content lowers trust. Review user-facing copy and proofread. | src/pages/Partner.tsx; src/components/restaurant/RestaurantCard.tsx | Open